Resource Manager

Iteration Plan

# 1. Key milestones

|  |  |
| --- | --- |
| **Milestone** | **Date** |
| Iteration start | 15 July 2019 |
| Sync Meeting | 19 July 2019 |
| All Core Project Use Cases met | 28 July 2019 |
| System user use cases fully defined | 28 July 2019 |
| Iteration End | 29 July 2019 |

# 2. High-level objectives

1. Begin IOCM Phase by Generating and Building objectives

# 3. Evaluation criteria

1. Core functionality for Projects fully functional
2. Design work for system user management is completed

# 4. Work Item assignments

The following Work Items will be addressed in this iteration:

|  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| **Work Item ID** | **Name or key words of description** | **Outcome** | **State** | **Assigned to (name)** | **Estimated Hours** | **Hours worked** | **Estimate of hours remaining** |
| 1.1 | Complete development of create project | Projects can be fully used within the system | Existing implementation to be verified | Brodie | 3 | 1 | 0 |
| 1.2 | Complete development of update project | Projects can be fully used within the system | Existing implementation to be verified | Brodie | 3 | 1 | 0 |
| 1.3 | develop unit test for project objects | Projects can be fully tested | [in repository](https://github.com/MatthewJuliusScott/ResourceManager/commit/97c20c1f7649b7501689bbf96ff81c6bb6da5e58) | Matt | 4 | 4 | 0 |
| 2.1 | complete development of add skill | Skills can be fully used within system | [in repository](https://github.com/MatthewJuliusScott/ResourceManager/commit/2312a6c9237a211c3f0b7f5bcec89965a940ac62) | Jack | 4 | 4 | 0 |
| 2.2 | complete development of update skill | Skills can be fully used within system | [in repository](https://github.com/MatthewJuliusScott/ResourceManager/commit/2312a6c9237a211c3f0b7f5bcec89965a940ac62) | Jack | 4 | 4 | 0 |
| 2.3 | complete development of remove skill | Skills can be fully used within system | [in repository](https://github.com/MatthewJuliusScott/ResourceManager/commit/2312a6c9237a211c3f0b7f5bcec89965a940ac62) | Jack | 4 | 4 | 0 |
| 2.4 | develop unit tests for skill objects | Skills are unit tested | [in repository](https://github.com/MatthewJuliusScott/ResourceManager/commit/79a0af5a9c2b11d9f23847ec932e78a0c68aea05) | Matt | 4 | 4 | 0 |
| 3.1 | create use case description for Add system users | Development of add system users can begin | [In repository](https://github.com/MatthewJuliusScott/ResourceManager/commit/f88352bbf8b8f7931032870a170d698495f0e883) | Brodie | 2 | 2 | 0 |
| 3.2 | create use case description for edit system users | Enable swift development of edit system users | [Complete](https://github.com/MatthewJuliusScott/ResourceManager/commit/dc3d12ae1fe38c1c46ee739838c072cd591e67b1) | Aaron | 2 | 1 | 0 |
| 3.3 | create use case description for remove system users | Enable swift development of Remove system users | [Complete](https://github.com/MatthewJuliusScott/ResourceManager/commit/dc3d12ae1fe38c1c46ee739838c072cd591e67b1) | Aaron | 2 | 1 |  |
| 3.4 | Develop wireframes for system user functionality | System user functionality can be developed against | Moved to next iteration |  |  |  |  |
| 3.5 | develop pages required for adding system users | Enable page functionality for managing system users | [Complete](https://github.com/MatthewJuliusScott/ResourceManager/commit/dc3d12ae1fe38c1c46ee739838c072cd591e67b1) | Aaron | 3 | 1.5 |  |
| 4.1 | develop wireframes for view upcoming projects | View upcoming projects can be developed against | Moved to next iteration |  |  |  |  |
| 4.2 | develop use case description for view upcoming projects | View upcoming projects can be developed against | Moved to next iteration |  |  |  |  |
| 5.1 | Iteration Manager | Enable the team to stay on task for the iteration |  | Aaron | 2 |  |  |
|  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |

# 5. Issues

|  |  |  |
| --- | --- | --- |
| **Issue** | **Status** | **Notes** |
| Server down | Unfinished | Server reset itself, no one could log on, Aaron was reimage servereverything, Matt will need to reinstall programs. |

# 6. Assessment

|  |  |
| --- | --- |
| Assessment target | fully functional basic system objects |
| Assessment date | 29/7/2019 |
| Participants | Matthew, Aaron, Brodie, Jack |
| Project status | Green |

## Assessment against objectives

## Work Items: Planned compared to actually completed

Work items 3.4, 4.1 and 4.2 were not completed this iteration. They have been moved to the next iteration.

## Assessment against Evaluation Criteria Test results

## Other concerns and deviations

There were some tasks that were overlooked/unassigned and forgotten about.