Resource Manager

Iteration Plan

# 1. Key milestones

|  |  |
| --- | --- |
| **Milestone** | **Date** |
| Iteration Sync Meeting | 23/9/19 |
| User Acceptance Testing complete | 7/10/19 |
| Beta UAT complete | 7/10/19 |
| Resolve any highlighted issues | 7/10/19 |

# 2. High-level objectives

1. System ready for deployment and testing
2. Alpha UAT completed
3. Documentation in Wiki as required

# 3. Evaluation criteria

1. System is accessible on main site
2. Beta UAT testers have tested system
3. Any new issues are resolved with time permitting.

# 4. Work Item assignments

The following Work Items will be addressed in this iteration:

|  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| **Work Item ID** | **Name or key words of description** | **Outcome** | **State** | **Assigned to (name)** | **Estimated Hours** | **Hours worked** | **Estimate of hours remaining** |
| 1.1 | Deploy System to production | System is available for testing | [Complete](https://ms.havealookdemo.com.au) | Matt | 1 | 1 | 0 |
| 1.2 | Ensure test users exist in production deployment | Testers can begin testing | [Complete](https://ms.havealookdemo.com.au/users/edit/39) | Aaron | 1 |  |  |
| 1.3 | Provide instructions for testing to testers | Testers can now test | [Complete](https://github.com/MatthewJuliusScott/ResourceManager/tree/master/Documentation/Beta%20Test%20Feedback) | Aaron | 1 |  |  |
| 1.4 | Resolve first batch of identified issues | Issues identified by the first wave of testing complete, This will expand into potentially more issues | Complete | Team | See Work items 4.x |  |  |
| 2.1 | Fix issue where new users couldn’t be created | Users can be added to the system | [Complete](https://github.com/MatthewJuliusScott/ResourceManager/commit/2f4c3764f9908a67aff8867505cca379a387cd95) | Matt | 3 | 3 |  |
| 3.1 | Create Letter of Acknowledgement. | Client can acknowledge the system created. | [Complete](https://github.com/MatthewJuliusScott/ResourceManager/blob/master/Documentation/LetterOfAcknowledgement.docx) | Jack | 1 | 1 | 0 |
| 4.1 | Alter heading to Link to resource | Easier to understand | [Complete](https://github.com/MatthewJuliusScott/ResourceManager/commit/ec0a255b7573173ebd6302463fceea81138da760) | Aaron | 1 | 1 | 0 |
| 4.2 | Better Error handling when end-date is earlier than start date | better UX | [Complete](https://github.com/MatthewJuliusScott/ResourceManager/commit/81c43fba4e2f0778227a97c17d33a28bc8ed9651) | Aaron | .5 | .5 | 0 |
| 4.3 | Date pickers allow changing of years | Dates can now span multiple years more easily | [complete](https://github.com/MatthewJuliusScott/ResourceManager/commit/db79c0e95c94003a2413c13c2663bb89ef88c34e) | Aaron | 2 | 2 | 0 |
| 4.4 | Add error handling for resource requirement hours | System doesn’t accept invalid values | [Complete](https://github.com/MatthewJuliusScott/ResourceManager/commit/81c43fba4e2f0778227a97c17d33a28bc8ed9651) | Aaron | 2 | 2 | 0 |
| 4.5 | Add some password enforcement | users can cleanly change passwords | [Complete](https://github.com/MatthewJuliusScott/ResourceManager/commit/2d41d0e171a08f3e28147b931ec5faadc4e57f7c) | Aaron | 2 | 2 | 0 |
| 4.6 | Sort users and resources alphabetically | Users and resources should be sorted alphabetically | [Complete](https://github.com/MatthewJuliusScott/ResourceManager/commit/a6c3f87717046291e3aa4f8f2aeded35a2cf3d95) | Aaron | 1 | 1 | 0 |
| 4.7 | Create successful password change pop up | People know when password changes appropriately | [Complete](https://github.com/MatthewJuliusScott/ResourceManager/commit/2d41d0e171a08f3e28147b931ec5faadc4e57f7c) | Aaron | 1 | 1 | 0 |
| 4.8 | New assignment notification not working | Users will correctly receive notifications on getting assigned | [Complete](https://github.com/MatthewJuliusScott/ResourceManager/commit/c2c527a532e3f7bce08480e8b3bb93f57c195fcd) | Matt | 1 | 1 | 0 |
| 4.9 | Password changed successfully pop-up always appears | Password changed successfully should only appear when password is changed | [Complete](https://github.com/MatthewJuliusScott/ResourceManager/commit/c2c527a532e3f7bce08480e8b3bb93f57c195fcd) | Matt | 1 | 1 | 0 |
| 4.10 | Required User inputs are not required in user edit / create form | Users will not be possible to create without required fields being input | [Complete](https://github.com/MatthewJuliusScott/ResourceManager/commit/c2c527a532e3f7bce08480e8b3bb93f57c195fcd) | Matt | 1 | 1 | 0 |
| 4.11 | There is no front end validation for user password and confirm password field | The form will be validated prior to submit to prevent having to re-enter data | [Complete](https://github.com/MatthewJuliusScott/ResourceManager/commit/c2c527a532e3f7bce08480e8b3bb93f57c195fcd) | Matt | 1 | 1 | 0 |
| 4.12 | Add timeframes and axis for charts. | Users will be able to select the timeframe of the chart reports, and see a month by month breakdown | [Complete](https://github.com/MatthewJuliusScott/ResourceManager/commit/6d5a6e218c43087312986fbff239f724be1dc2f5) | Matt | 12 | 12 | 0 |
| 4.13 | Add POB field to project, must be a unique field | POB stands for Performance Obligation which is essentially a cost-code, would be up to 16 chars long, but they look something like this: 7812036 or 7812038 | [Complete](https://github.com/MatthewJuliusScott/ResourceManager/commit/2d95e67dec31ab9118fe3e541e7e6d2d017c9624) | Matt | 1 | 1 | 0 |
| 4.14 | Enhancement to notification of new allocation | New allocation notification has been expanded to provide more information to the user | [Complete](https://github.com/MatthewJuliusScott/ResourceManager/commit/1c72d458d9f111a32587bb5d8b06b2e9bc0af695) | Brodie | 0.5 | 0.5 | 0 |
| 4.15 | User cannot be linked to resource without also changing password | Users can be linked to a resource independent of password reset | In progress | Brodie | 1 | 2 | 1 |
| 4.16 | Fixed up html for Edit Users page. | Form layout is consistent. | [Complete](https://github.com/MatthewJuliusScott/ResourceManager/commit/027e5f752dc27e96080b55772f28a898abd869db) | Jack | 0.2 | 0.2 | 0 |

# 5. Issues

|  |  |  |
| --- | --- | --- |
| **Issue** | **Status** | **Notes** |
|  |  |  |
|  |  |  |

# 6. Assessment

|  |  |
| --- | --- |
| Assessment target | Initial transition complete |
| Assessment date | 10/11/2019 |
| Participants | Matthew, Aaron, Brodie, Jack |
| Project status | Green |

## Assessment against objectives

We believe we have achieved all outcomes from this iteration

## Work Items: Planned compared to actually completed

All work items on the items list were completed except for one outstanding issue

## Assessment against Evaluation Criteria Test results

The system is accessible

Beta testers have completed testing and provided feedback

Identified issues within scope have been resolved

## Other concerns and deviations