Resource Manager

Iteration Plan

# 1. Key milestones

|  |  |
| --- | --- |
| **Milestone** | **Date** |
| Iteration start | 27 May 2019 |
| Application development for existing use cases completed | 3 June 2019 |
| Developed design documentation for Authentication use case | 3 June 2019 |
| Application Logo identified | 7 June 2019 |
| Application development complete for Authenticate with system use case | 9 June 2019 |
| Design documentation for View User allocation created | 9 June 2019 |
| design documentation for view unassigned resources created | 9 June 2019 |
| Deploy current application to environment | 10 June 2019 |
| Iteration Complete | 10 June 2019 |

# 2. High-level objectives

1. Users will be able to add and remove skills
2. Application will have appropriate branding
3. Authentication for system will work
4. Design documentation for next iteration complete
5. System deployed to environment

# 3. Evaluation criteria

1. System will be deployable
2. Deployable architecture will include update and remove skills
3. Logo located in appropriate locations
4. Documentation ready for next iteration
5. System is reachable and can be logged on to.

# 4. Work Item assignments

The following Work Items will be addressed in this iteration:

|  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| **Work Item ID** | **Name or key words of description** | **Outcome** | **State** | **Assigned to (name)** | **Estimated Hours** | **Hours worked** | **Estimate of hours remaining** |
| 1.1 | Develop business logic for update skills |  |  |  |  |  |  |
| 1.2 | Develop Page for update skills |  |  |  |  |  |  |
| 1.3 | Develop page for Remove skills |  |  |  |  |  |  |
| 1.4 | Develop business logic for remove skills |  |  |  |  |  |  |
| 2.1 | Design logo for use |  |  |  |  |  |  |
| 2.2 | Approve logo |  |  |  |  |  |  |
| 2.3 | Approve logo |  |  |  |  |  |  |
| 2.4 | Approve logo |  |  |  |  |  |  |
| 3.1 | Complete full use case description for Authenticate with system |  |  |  |  |  |  |
| 3.2 | Complete wireframes for Authenticate with system |  |  |  |  |  |  |
| 3.3 | Develop and implement business logic for Authenticate with system |  |  |  |  |  |  |
| 3.4 | Construct login page |  |  |  |  |  |  |
| 4.1 | Full use case Description for View User allocation complete |  |  |  |  |  |  |
| 4.2 | Wireframes for view user allocation |  |  |  |  |  |  |
| 4.3 | Full use case description for view unallocated resources |  |  |  |  |  |  |
| 4.4 | Wireframes for view unallocated resources complete |  |  |  |  |  |  |
| 5.1 | Prepare and configure system for deployment |  |  |  |  |  |  |
| 5.2 | deploy system |  |  |  |  |  |  |
| 5.3 | Test existing system |  |  |  |  |  |  |
| 5.4 | Confirm system is running an usable via basic login and test |  |  |  |  |  |  |
| X | Iteration Manager |  |  |  |  |  |  |

# 5. Issues

|  |  |  |
| --- | --- | --- |
| **Issue** | **Status** | **Notes** |
| lack of communication during iterations | ongoing | Team needs to be more committed to ensuring other team members are notified of completion of activities |

# 6. Assessment

|  |  |
| --- | --- |
| Assessment target | Have system up and running for login. |
| Assessment date | 10/6/2019 |
| Participants | Matthew, Aaron, Brodie, Jack |
| Project status | Yellow |

## Assessment against objectives

## Work Items: Planned compared to actually completed

## Assessment against Evaluation Criteria Test results

Currently all assessment items are certified as complete except for:

## Other concerns and deviations

Primary concern is still a lack of communication for the team.

While a lot of work has been accomplished this iteration we are still at least an iteration behind.