Resource Manager

Iteration Plan

# 1. Key milestones

|  |  |
| --- | --- |
| **Milestone** | **Date** |
| Iteration start | 10 June 2019 |
| Complete end to end UAT of CCRD Use Case | 16 June 2019 |
| Ensure LCAM is met | 20 June 2019 |
| Complete elaboration Phase assessment | 23 June 2019 |
| Iteration End | 24 June 2019 |

# 2. High-level objectives

1. Deliver LCAM

# 3. Evaluation criteria

1. All Criteria of LCAM met
2. Documentation is in a strong position.

# 4. Work Item assignments

The following Work Items will be addressed in this iteration:

|  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| **Work Item ID** | **Name or key words of description** | **Outcome** | **State** | **Assigned to (name)** | **Estimated Hours** | **Hours worked** | **Estimate of hours remaining** |
| 1.1 | Perform all CCRD UAT tests |  | [Complete](https://github.com/MatthewJuliusScott/ResourceManager/commit/ba22d1b79f293db037dca1d109d98766efb684ba) | Aaron | 2 | 2 |  |
| 1.2 | Perform all CCRD UAT tests as project Sponsor |  | [Complete](https://github.com/MatthewJuliusScott/ResourceManager/commit/ba22d1b79f293db037dca1d109d98766efb684ba) | Aaron | 2 | 3 |  |
| 1.3 | Create unit tests security and functionality of each controller | [In repository](https://github.com/MatthewJuliusScott/ResourceManager/commit/deab2b8942459e3bc9263da27928d5507b06b285) | Complete | Matt | 8 | 8 | 0 |
| 1.4 | Create integration tests for CCRD and CCRD alternate flow | [In repository](https://github.com/MatthewJuliusScott/ResourceManager/commit/24ea8205cbee70803a7301901290130d0df9cc11) | Complete | Matt | 4 | 4 | 0 |
| 1.5 | Run tests for allocate Skills business case |  | Complete | Brodie | 2 | 2 |  |
| 2.1 | Complete elaboration Phase assessment |  | [Complete](https://github.com/MatthewJuliusScott/ResourceManager/blob/master/Documentation/Inception%20Phase%20Status%20Assessment%20-%20LCAM.docx) | Aaron | 2 | 2 |  |
| 2.2 | Complete elaboration Phase assessment |  | [Complete](https://github.com/MatthewJuliusScott/ResourceManager/blob/master/Documentation/Inception%20Phase%20Status%20Assessment%20-%20LCAM.docx) | Matt | 2 | 2 |  |
| 2.3 | Complete elaboration Phase assessment |  | [Complete](https://github.com/MatthewJuliusScott/ResourceManager/blob/master/Documentation/Inception%20Phase%20Status%20Assessment%20-%20LCAM.docx) | Jack | 2 | 2 |  |
| 2.4 | Complete elaboration Phase assessment |  | [Complete](https://github.com/MatthewJuliusScott/ResourceManager/blob/master/Documentation/Inception%20Phase%20Status%20Assessment%20-%20LCAM.docx) | Brodie | 2 | 2 |  |
| 3.1 | Develop and implement business logic for Authenticate with system |  | [Complete](https://github.com/MatthewJuliusScott/ResourceManager/commit/deab2b8942459e3bc9263da27928d5507b06b285) | Matt | 4 | 4 | 0 |
| 4.0 | Review and update (as required) project vision |  | [Complete](https://github.com/MatthewJuliusScott/ResourceManager/blob/master/Documentation/Vision.docx) | Aaron | 2 | 2 |  |
| 4.1 | Review and Update (as required) Requirement Model |  | Complete | Jack | 2 | 2 |  |
| 4.2 | Review and update Risk List |  | Complete | Brodie | 2 |  |  |
| 4.3 | Review and update Proposed Architecture |  | [Complete](https://github.com/MatthewJuliusScott/ResourceManager/blob/master/Documentation/Architecture%20Notebook.doc) | Aaron | 2 |  |  |
| 4.4 | Review and Update Master Test plan |  | Complete | Jack | 3 | 3 |  |
| X | Iteration Manager |  | Complete | Aaron | 3 | 3 |  |
| 5 | Record Demo video |  | [Complete](https://drive.google.com/file/d/1qJmdeRYm4EP7SIeyJj4gi-4GmNXwwy4q/view?usp=sharing) | Aaron | 2 | 4 |  |
|  |  |  |  |  |  |  |  |

# 5. Issues

|  |  |  |
| --- | --- | --- |
| **Issue** | **Status** | **Notes** |
| lack of communication during iterations | ongoing:amber | Team needs to be more committed to ensuring other team members are notified of completion of activities |

# 6. Assessment

|  |  |
| --- | --- |
| Assessment target | Have system up and running for login. |
| Assessment date | 10/6/2019 |
| Participants | Matthew, Aaron, Brodie, Jack |
| Project status | Yellow |

## Assessment against objectives

This Iteration LCAM was realised.

We have performed UAT of the CCRD use case with our stakeholders and passed all tests.

## Work Items: Planned compared to actually completed

All work items were completed this iteration

## Assessment against Evaluation Criteria Test results

All items completed

## Other concerns and deviations

Primary concern is still a lack of communication for the team.