## Sheet1
Item | User Feedback | Team understanding of required change | Decision | Result
1 | Yes, was able to change password, although there was no confirmation popup or message to say that it had changed correctly, just reset the page. I checked by trying to use old password to change again, but got an error message, so clearly had changed. | Create password changed sucessfully pop-up | Approved for implementation, ideally should have already been part of application | Pop-up created
2 | When the user was created, I was expecting to see a list sorted alphabetically, rather than based on create date – thinking about when there could be thousands of resources. | Users and Resources should be sorted alphabetically | Approved for implementation | Items are sorted accordingly
3 | Reverse the way users and resources are linked | Make all resources have a user location | Declined for implementation, the reason for the way the implementation was made is because not all users must be resources | No action taken
4 | Allow start date for resource requirement to be in the past | Resource requrements should be able to be retroactively filled | Could not reproduce bug | No action taken
5 | If I change the password, the new password and confirm password don’t have to match. Fairly sure it uses the “confirm password” as your password. | Apply data validation to Password fields | Approved for implementation | Front and back end validation performed
6 | Alter heading to 'link to resource" | change the wording for linking a user to a resource be called 'link to resource' | approved for implementation, minor change | page updated
7 | The charts need axes and a title, not sure what the timeframe of the report is. | Add user input to allow selecting a timeframe | approved for implementation | page updated
8 | I managed to put an end date before the startdate and got a 500 error code. - Richard feedback | Stop a user from entering a start date after an end date | Could not reproduce bug | No action taken
9 | user can enter negative resource requirement hours | Add data validation to resource requirements | approved for implementation | page updated
10 | projects with the same name can be created | Projects should be unique | Discussed with sponsor for clarification, as long as a unique key is available it will be suitable, Also he requested a POB field to be added | Project model updated and pages updated to include new field
11 | Date pickers do not allow changing years | Update date pickers so years can be easily selected | Approved for implementation | pages updated
12 | implement new resource view | Add resource view for resources and what assignments they have | denied, out of scope of project | N/a