## Instructions
RISK MANAGEMENT LOG
Column | Instructions For Completing This Document
Complete the Project Name, NC, Project Manager Name, and Project Description fields
For each risk identified, complete the following:
A | ID: A unique ID number used to identify the risk in the risk tracking log.
B | Current Status: This column should be populated with the risk's current status. o Open: The risk is currently open but is not yet an issue. o Closed: The risk is no longer considered an active project threat and can be closed with or without resolution.
C | Risk Impact: This column should be populated with the potential impact of the risk if it did become a project issue. Valid options include the following: High, Medium, Low. These are defined as follows: o High: Risk that has the potential to greatly impact project cost, project schedule or performance. o Medium: Risk that has the potential to slightly impact project cost, project schedule or performance. o Low: Risk that has relatively little impact on cost, schedule or performance.
D | Probability of Occurrence: This column should be populated with the estimated probability that the risk will at some point become a project issue.
E | Risk Map: This is a calculated field based on the values selected for both Risk Impact and Probability of Occurrence. o Green: LL (Low Probability, Low Impact), LM (Low Probability, Medium Impact), ML (Medium Probability, Low Impact) o Yellow: LH (Low Probability, High Impact), MM (Medium Probability, Medium Impact), HL (High Probability, Low Impact) o Red: MH (Medium Probability, High Impact), HM (High Probability Medium Impact), HH (High Probability, High Impact)
F | Risk Description: This column should be populated with a description of the risk.
G | Project Impact: This column should be populated with a description of the potential project impact as a result of the risk.
H | Risk Area: This column should be populated with the appropriate risk area.
I | Symptoms: This column should be populated with the symptoms of risk that may eventually lead to the execution of a risk contingency plan.
J | Trigger: This column should be populated with the triggers that would indicate the requirement to execute contingency plans.
K | Risk Response Strategy: This column should be populated with the preferred risk response strategy.
L | Response Strategy: This column should be populated an appropriate response strategy to prevent the risk from becoming an issue.
M | Contingency Plan: This column should be populated with a description of the risk contingency plan.
Column | Instructions For Changing the Contents of Drop-Down Menus
C, D, H | Highlight the cell of which you wish to change the content of the drop down menu. From the file menu click "Data" -> "Validation" and change the content of the source field
Column | Instructions For Filtering Data
Any | Highlight the header of the cell you wish to filter data on From the file menu click "Date" -> "Filter" ->"Auto Filter" Then select your filter criteria from the drop down menu that appears on your header cell

## Risk_Tracking_Log
RISK MANAGEMENT LOG | [7 empty] | RISK MANAGEMENT LOG
Project Name: |  |  | Resource Manager |  |  |  |  | Project Name: | Resource Manager
National Center: |  |  | <required> |  |  |  |  | National Center: | <required>
Project Manager Name: |  |  | Team Managed Project |  |  |  |  | Project Manager Name: | Team Managed Project
Project Description: |  |  | A tool which can assist a workteam with resource allocation among projects |  |  |  |  | Project Description: | A tool which can assist a workteam with resource allocation among projects
ID | Current Status | Risk Impact | Probability of Occurrence | Risk Map | Risk Description | Project Impact | Risk Area | Symptoms | Triggers | Risk Response Strategy | Response Strategy | Contingency Plan
1 | Open | High | Low | Yellow | Team does not have an adequete skill set to complete this project. Team members have a varying level of experience in projects of this sort and in using the technologies required. Time will have to be set aside for retraining and upskilling of team members to allow work on the project to proceed. | If team members are not able to develop the skills needed to proceed with the project, then work may fall behind schedule or stop entirely due to lack of ability to proceed. | Project Resources Schedule | Team members are unable to proceed with project development due to lack of skill/confidence with technologies used. | Team is unable to identify appropriate technologies prior to start date for development work/Team fails to reach development milestones due to lack of ability to use technologies needed. | Mitigation | Identify skills and technologies required along with means of upskilling team members to use these technologies. | Find alternative technologies which team members are able to use.
2 | Open | Low | Low | Green | Project Sponsor withdraws support for the project. As this project is being done for an external sponsor, it is possible that during the course of development the sponsor may decide that they no longer wish to make use of the final product. This will not neccesarily impact the project being completed however it may impact other areas of the development process. | If the Sponsor pulls out of the project, this may leave the team without a clear picture of the requirements of the project or the overall goal. Due to this project also serving as an assessment item this will not however result in the cancellation of the project or prevent the team from completing the project. | Project Resources Schedule | Project Sponsor is no longer supportive of the project or expresses that they no longer require the final product due to changing needs. | Sponsor contacts the project team advising that they no longer wish to support the project. | Acceptance | Continue to work regardless as this is not a risk under control of the team not would it cause the project to be canceled. | Team can conntinue work if the sponsor pulls out using requirements as communicated by the sponsor prior to this occurring.
3 | Open | High | Low | Yellow | Team members leave the project team. As this project is being done by a small team, the possibility of one of the team members leaving the project/subject/course may have a serious impact on the overall project and the work done by other team members. This is an unlikely possibility however it is possible to plan work to avoid this from being an issue that would prevent the project from being completed. | If a team member/members leaves the project, this will cause the amount of work required by the remaining members to increase significantly, and will cause significant changes to work plans to accommodate this. This may cause delays or at worst, a failure to complete the project entirely. | Project Resources Schedule Team Members | Team member leaves the project team due to a desire to no longer continue with the project/subjec/course. | Team member advises the other members of the team that they are leaving the project. | Mitigation | Plan work items and milestones so that each team member is capable of taking up additional work if this scenario does occur. Ensure that work done is understandable by all other team members to allow them to pick up where others left off. | Team must be able to adapt work plans and milestones to account for changes in team structure. or reduce scope in negotiation with the sponsor where possible to deliver a minimum viable product
4 | Open | Medium | Low | Green | Final product is rejected by the project sponsor. If the final product is not up to the quality expected by the project sponsor then it may be rejected for use. As this project serves both the purpose of providing a product for the sponsor and as an assessment item this will not neccesarily make the project a failure however it would be considered a very negative outcome. Communication with the sponsor and effective planning to ensure the product meets the expectations of the sponsor will offset this risk. | This would mean that the final product delivered to the project sponsor does not meet their standards or requirements, and is therefore rejected after completion of the majority of project work. This would mean that the project has failed at some point to meet or to adequetly identify project requirements and specifications. | Project Resources Project Sponsot Final Product | Sponsor seems unsatisfied with the final product approaching the deadline, key requirements may not have been meant. | Project sponsor informs the team after delivery of the final product that it does not meet their expectations. | Mitigation | Ensure communication with the sponsor to ensure that the project requirements are understood and that expectations for the final product are understood. | Ensure that product and associated documentation is produced that meets assessment requirements to fulfil the assessment component of this project. As well as gaining feedback iteratively from the sponsor to ensure that their requirements are being met
5 | Open | High | Low | Yellow | The final product is unable to ensure the security of user information and prevent unauthorised users from gaining access. Due to this project being intended for use in a corporate environment a lack of adequete security ould pose a risk of sensitive employee information being exposed to unauthorised users. This can be managed through ensureing appropriate security features are properly assessed and implemented. | If the final project creates a risk for the sponsor by failing to protect user security then it may be rejected by the sponsor or considered a failure in general due to the importance of this requirement. | Project Resources Project Sponsot Final Product | Security concerns become apparent in reviews of project components throughout the development process. | Review/testing of the final product reveals significant areas of risk for breaches of private user data. | Mitigation | Establish strong requirements for security of users and investigate means of effectively meeting these requirements with the technologies used. | Incorporate tools to protect user security from a third party or remove features which contribute to the security risks if no solution can be found.
6 | Open | High | Low | Yellow | Final product is incompatible with the clients systems, either in terms of operating system or primary devices. According to the project requirements, this project should be compatible with desktop and laptop computers, and accesible without access to the company's network. There is a possibility that the final product does not meet these requirements, which can be mitigated by assessing the capabilities of the technologies used by the team and selecting technologies which are known to be meet these requirements. | Incompatibility with the client's existing infrastucture would meant the final product is useless to the client, which would mean that the project will fail to deliver a useable product to the sponsor. | Proejct Resources Projec Sponsor Final Product | Investigation of technologies reveals incompatibilities with systems used by the client | Testing of the final product reveals that it is incompatible with the clients existing environment. | Mitigation | Plan to allow for the final product to be compatible with clients systems based on communication with the project sponsor. | Identify means of establishing compatibility between the systems using external software/technoloy.
7 | Open | High | Low | Yellow | Product is incapable of providing needed functionality to the client (including ability to adequetly track user skills, identify skills needed for projects, or match users to projects based on their skills). This could be due to a failure to properly implement these features properly by the project team, or due to the technologies used not being able to provide these features, in both cases this would represent a failure to deliver the expected service to the sponsor. This can be mitigated by properly establishing the project requirements and selecting technologies that can deliver the services required. | If the final product does not adequately deliver the expected functionality to the client, it may be rejected by the client and will therefore be considered a failure. | Project Sponsor Final Product | System components are unfinished or non-functional approaching the deadline for their completion. | Failure to complete critical work items or to reach important iteration milestones. | Mitigation | Properly identify all project requirements and make the documentation identifying these requirements accessible to all team members. | Refocus project goals to allow for most neccesary requirements to be fulfilled.
8 | Open | High | Low | Yellow | Project team is unable to identify or procure technologies which allow the planned features of the product to be implemented fully. If the team is unable to determine which technologies should be used to implement the project, then it will not be able to proceed beyond the primary planning stage, resulting in the project failing. In order to avoid this it is neccesary for the appropriate investigation into this area to be conducted thoroughly and early. | If a suitable technology or platform for the project is not found, then the project will not be able to deliver a tangible product at the end and cannot proceed beyond the planning stages. | Project Resources | Team is uncertain as to which technologies will be used during the planning phase of the project. | Planning phase of the project is concluded with no clear decision made on which technologies are to be used to meet project requirements. | Mitigation | Conduct thorough investigation into appropriate technologies to meet project needs. | Make use of third-party systems where possible to allow work to continue.
9 | Open | Medium | Low | Green | System is unable to meet the reliabilty requirements of the project specifications due to technical limitations or lack of planning. This would result in the final project being largely functional however it would provide sub-optimal service. Sufficient testing and refining of the end product can be used to avoid this. | If the final product cannot perform reliably after project completion, then it may cause the sponsor loss of productivity and will mean that the product delivered is of a significantly lower quality. | Project Sponsor Final Product | Testing reveals multiple potential or actual issues with system reliability. | Final product is handed over to the client while reliability issues are present. | Mitigation | Make use of thorough testing and review of the project to ensure that issues can be identified and corrected. | Identify potential means of using the software to minimise issues during use.
10 | Open | Medium | Low | Green | System is unable to meet performance requirements due to technical limitations or lack of planning to accommodate this. This would result in a sub-optimal product being delivered at the conclusion of the project. May be avoided by thorough testing and refining of the final product to address any causes of loss of performance. | Failure to meet performance requirements will result in a poor quality product being delivered at the conclusion of the project. | Project Sponsor Final Product | Testing reveals multiple potential or actual sources of performance loss. | Final product is handed over to the client while performance issues are present. | Mitigation | Make use of thorough testing and review of the project to ensure that issues can be identified and corrected. | Identify potential means of using the software to minimise issues during use.
11 | Open | Medium | Low | Green | Project requirements are not adequetly communicated to all team members, resulting in unclear development goals and poorly-defined project scope. If all team members are not adequetly aware of the requirements of the project, then they may not be able to effectively meet these requirements. This can be addressed through proper planning and ensuring frequent and effective communication between all team members. | Team members not having a clear picture of the project requirements during the development process will make it more likely that the final product is not able to meet these requirements, potentially causing a sub-optimal final product or even project failure. | Team Members Final Product | Team members express that they are unsure of the requirements that they should be working towards. | Final product fails to meet numerous functional and nn-functional requirements. | Mitigation | Ensure that thorough planning and documentation is done to identify project requirements and make documentation accessible to all team members to be reviewed as needed. | Team members will need to identify the most neccesary requirements to be worked towards fulfilling to ensure project progress.
12 | Open | Medium | Low | Green | Project Scope is not clearly set causing scope creep. This would cause the work done by the project team to be unfocused and directed towards goals which exceed the neccessary scope of this project, potentially causing work milestones to be missed. This can be avoided through proper planning and establishing of the overall project scope. | If the project scope becomes unfocused or suffers from scope creep, the project goals may exceed what is possible within the given time frame or using the resources available. | Project Resources Team Members Schedule | Team members express that they do not understand the project scope adequetly. | Project fails to meet important development milestones on time due to additional work taking time from more neccesary tasks. | Mitigation | Establish a clear understanding of project scope and communicate this clearly to all team members. | Refocus project scope and establish new planning documentation as neccesary to support this.
13 | Open | High | Low | Yellow | Improper version control procedures cause disruption to workflow or potential loss of work. Failure by team members to follow common procedures when updating to version control may cause confusion and potentially loss of work due to version conflicts. Depending on the areas affected this could cause significant risk to the project as a whole. To avoid this the team should establish and follow set rules for updating the master branch of version control. | All project work is to be shared and stored using proper version control to maintain data integrity and a clear and consistent tracking of work done. Not using proper version control practice will cause the project work to suffer and result in loss of productivity. | Project Resources Team Members Schedule | Proper version conrtol procedures are not consistently upheld by all users. | Data loss occurs due to improper use of version control. | Mitigation | Ensure that all team members are aware of and follow appropriate version control procedures at all times. | Ensure that backups are available either through the hosting service or through team members manually preparing backups of version control.
14 | Open | Medium | Low | Green | Chosen technology stack has a too high cost to implement when standing up final product. This would mean that the final product cannot be delivered to the client or provide the services expected, making the project a failure. Investigating and identifying appropriate hosting solutions is therefore a neccesary part of the planning phase of this project in order to avoid this. | Project team willl be required to invest their own money | Project Resources | Free hosted solutions are not viable | Hosting service does not meet performance requirement | Mitigation | Investigate free hosting solutions early | ensure that one of the free technologies will meet the needs of the project
15 | Open | Low | Low | Green | Conflicts between team members cause disruptions/delays in reaching project goals. If conflict arises between team members as to how a certain feature should be implemented or how development of the project should proceed, then this may cause delays in completing work items by the deadlines set. To avoid this team members should be aware of each other's roles and responsibilities and follow conflict resolution procedures as outlined in the team charter. | Disputes may result in delays in project work which may be compounded if team members do not follow appropriate conflict resolution procedures. | Project Resources Team Members Schedule | Conflict arises between team members which causes delays in achieving work items. | Deadline for work items is not met due to conflict. | Mitigation | Conflict resolution procedures are outlined in the team charter. | Expand team discussions to investigate further options for moving the project forward/reassess current work item objectives.
Note on A6: • ID: A unique ID number used to identify the risk in the risk management log.
Note on B6: • Current Status: This column should be populated with the risk's current status. o Open: The risk is currently open but is not yet an issue. o Closed: The risk is no longer considered an active project threat and can be closed with or without resolution.
Note on C6: • Risk Impact: This column should be populated with the potential impact of the risk if it did become a project issue. Valid options include the following: High, Medium, Low. These are defined as follows: o High: Risk that has the potential to greatly impact project cost, project schedule or performance. o Medium: Risk that has the potential to slightly impact project cost, project schedule or performance. o Low: Risk that has relatively little impact on cost, schedule or performance.
Note on D6: • Probability of Occurrence: This column should be populated with the estimated probability that the risk will at some point become a project issue. o High: Greater than 70% probability of occurrence. o Medium: Between 30% and 70% probability of occurrence. o Low: Below 30% probability of occurrence.
Note on E6: • Risk Map: This is a calculated field based on the values selected for both Risk Impact and Probability of Occurrence. o Green: LL (Low Probability, Low Impact), LM (Low Probability, Medium Impact), ML (Medium Probability, Low Impact) o Yellow: LH (Low Probability, High Impact), MM (Medium Probability, Medium Impact), HL (High Probability, Low Impact) o Red: MH (Medium Probability, High Impact), HM (High Probability Medium Impact), HH (High Probability, High Impact)
Note on F6: • Risk Description: This column should be populated with a description of the risk.
Note on G6: • Project Impact: This column should be populated with a description of the potential project impact as a result of the risk.
Note on H6: • Risk Area: This column should be populated with the appropriate risk area.
Note on I6: • Symptoms: This column should be populated with the symptoms of risk that may eventually lead to the execution of a risk contingency plan.
Note on J6: • Triggers: This column should be populated with the triggers that would indicate the requirement to execute contingency plans.
Note on K6: Risk Response Strategy: This column should be populated with the preferred risk response strategy.
Note on L6: • ResponseStrategy: This column should be populated an appropriate response strategy to prevent the risk from becoming an issue.
Note on M6: • Contingency Plan: This column should be populated with a description of the risk contingency plan.

## DropDown_Elements (hidden)
Risk Area
Schedule
Initial Costs
Life-cycle Costs
Technical Obsolescence
Feasibility
Reliability of Systems
Dependencies/Interoperability
Surety Considerations
Future Procurements
Project Management
Overall Project Failure
Organizational/Change Management
Business
Data/Information
Technology
Strategic
Security
Privacy
Project Resources